## Sheet2
[21 empty] | 2026 | [8 empty] | 2027 | [11 empty] | 2028
[21 empty] | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | Total
Region Name | Client Name | Project Name | Date of Work Order | Time Limit (in Month) | Stipulated Date of Completion | Target Date of Completion | Target Time Limit (In Month) | Team Leader/Project Manager | Residential Engineer | Design Engineer | Site Engineer | Misc Exp | Staff Exp. | Total Project Cost | completed work amt | remaining work amt | Total Fee | Proposed / Due Bill Amount | fee recvd | remaing fee
Rajkot | Gujarat State Police Housing Corporation(RR) | Design & PMC - Surat Division (Tribal School Development) | 2026-04-01 | 12 | 2027-03-31 23:48 | 2027-09-30 11:43 | 17.9873 | 0.5 | 0.4 | 0.3 | 0.35 | 0.05 | 1.6 | 22000 | 15000 | 7000 | 49.9994 | 5.56 | 0 | 49.9994 |  |  |  | 2.7777 | 2.7777 | 2.7777 | 2.7777 | 2.7777 | 2.7777 | 2.7777 | 2.7777 | 2.7777 | 2.7777 | 2.7777 | 2.7777 | 2.7777 | 2.7777 | 2.7777 | 2.7777 | 2.7777 | 2.7777 |  |  |  | 49.9994
Rajkot | Gujarat Urban Development Mission(RR) | Design - Kutiyana UGD Project | 2026-06-01 | 3 | 2026-08-31 05:57 | 2026-10-15 20:56 | 4.4968 | 0.5 | 0 | 0.3 | 0 | 0.1 | 0.9 | 842.54 | 0 | 842.54 | 10.1105 | 0 | 0 | 10.1105 | 2026 9: 2.5276; 2026 10: 2.5276; 2026 11: 2.5276; 2026 12: 2.5276 | 10.1105
Rajkot | Gujarat Urban Development Mission(RR) | Design - Kalwad Ws Project | 2026-02-01 | 3 | 2026-05-03 05:57 | 2026-06-17 20:56 | 4.4968 | 0.5 | 0 | 0.3 | 0 | 0.1 | 0.9 | 715.11 | 0 | 715.11 | 8.58 | 1.72 | 6.86 | 1.72 | 2026 4: 3.43; 2026 5: 3.43; 2026 6: 1.72 | 8.58
61.8299
[13 empty] | 5 | [5 empty] | Total Income per Month |  | 3.43 | 3.43 | 1.72 | 2.7777 | 2.7777 | 5.3054 | 5.3054 | 5.3054 | 5.3054 | 2.7777 | 2.7777 | 2.7777 | 2.7777 | 2.7777 | 2.7777 | [9 empty] | 52.0234
[21 empty] | 30.61 | 30.36 | 30.31 | 15.56 | 15.37 | 14.66 | 13.21 | 13.21 | 10.81 | 10.02 | 9.91 | 9.98 | 7.49 | 6.49 | 6.27 | [9 empty] | 224.26
[21 empty] | -27.18 | -26.93 | -28.59 | -12.7823 | -12.5923 | -9.3546 | -7.9046 | -7.9046 | -5.5046 | -7.2423 | -7.1323 | -7.2023 | -4.7123 | -3.7123 | -3.4923 | [9 empty] | -172.2366
[21 empty] | -27.18 | -54.11 | -82.7 | -95.4823 | -108.0745 | -117.4291 | -125.3338 | -133.2384 | -138.7431 | -145.9853 | -153.1176 | -160.3198 | -165.0321 | -168.7443 | -172.2366
Formulas:
Stipulated Date of Completion = [Date of Work Order]+([Time Limit (in Month)]*30.416)
Target Date of Completion = [Date of Work Order]+(([Time Limit (in Month)]*1.5)*30.416)